## Members
GCDE Awards Subcommittee
Name |  | Email | Cell/Telephone | Other
Chair:
| Yvonne Bussler White | yvonne.busslerwhite@dshs.wa.gov | 509-322-3764
Vice Chair:
| Matt Nash | mn73102000@gmail.com | 509-947-3428
Member:
| Amy Cloud | cloudamyx@gmail.com | 360-318-4356
| Lucas Doelman | lucasdoelman@gmail.com | 360-870-7318
| Clarence Eskridge | c.eskridge-gcdewa@outlook.com | 253-256-1804
| Cullyn Foxlee | cullyn@zohomail.com | 360-461-1114
| Kevin Frankeberger | k_frankeberger@yahoo.com | 360-426-8389
| Daniel Ledgett | d_ledgett@hotmail.com | 360-431-8958
| Tammy Stevens | Tammy.stevens@ofm.wa.gov | 360-764-6409
| Janet Bruckshen | jbruckshen@wvs.org | 425-948-5225
| Damiana Harper | damiana.harper@dsb.wa.gov | 509-381-6061
GCDE Staff:
| Ryan Bondroff | Ryan.Bondroff@esd.wa.gov | 360-801-5771 (Text only)
| Emily Heike | emily.heike@esd.wa.gov | 360-819-3772
| Elaine Stefanowicz | elaine.stefanowicz@esd.wa.gov | 360-706-3671
| Elizabeth Gordon | elizabeth.gordon@esd.wa.gov | 360-915-3465

## Workgroups
Work Groups
1. Correspondence – (1 -2 people) review, update sponsorship letter and create thank you letter templates:
Sign ups – Yvonne, Janet, Amy.
2. Marketing Outreach – (1-3 people) marketing / outreach for event in the event area; connect with partners, public, counties, schools…etc. (will be important esp. if partnering):
Sign ups – Cullyn, Emily, Amy, ESD videos . Kevin TBD (prefers to decide venue 1st).
3. Publications - (1-3 people) review brochure / PowerPoint /email teasers/programs/certificates/trophies:
Sign ups – Janet, Amy, Cullyn, and Tammy, Emily. Kevin TBD (prefers to decide venue 1st).
4. Event Logistics – (1-3) Planning Day of activities (speakers etc., recapped - photograhper/emcee secured, need to reach out to past recipients and vocalist):
Sign ups – Cullyn can start (bandwidth in late Feb – early March, may need someone else to carry things fwd), Yvonne, Tammy before July, Ryan, Matt, Daniel
5. Judging Panel (4-8) – scheduling & judging nominees:
Sign ups – Cullyn, Kevin, Matt, Janet, Daniel, Emily, and Clarence.
6. Nominee tracker to assist Emily – (1-2) asst. with contacting nominees and tracking info:
Sign ups – Matt, Yvonne

## January Tasks
2024 Awards Timeline Workplan
Meeting Date: Jan 4, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
3 year event location plan discussion | subcommittee
Select a Theme for the Awards Program | subcommittee | 2024-01-04
Select event location | Subcommittee | 2024-01-04
Select event venue | Subcommittee | 2024-01-04
travel reimbursements for guest speakers/nominees | subcommittee
In person event volunteers | subcommittee | 2024-01-04
Form marketing & outreach team | subcommittee | 2024-01-04 |  | marketing / outreach for event; partnering with other events
Form Publications team | subcommittee | 2024-01-04 |  | brochure / powerpoint /email teasers /programs/certificates | developed save the date flyer
Form Event logistis team | subcommittee | 2024-01-04 |  | Day of the event activities - vocalist, guest speakers, photographer, registration etc | MC - Phill White; photograhper Mary Crago; All Subcommittes present
Form judging panel team | subcommittee | 2024-01-04 |  | scheduling & judging nominees
Nominee tracker identified | subcommittee | 2024-01-04 |  | asst with contacting nominees and tracking info
Form correspondence team | subcommittee | 2024-01-04 |  | sponsor and thank letter templates
Photo session with the Governor with 2020-2023 Award recipients and their employers - status | Elizabeth
Governor invitation/photo session | Elizabeth
Sponsorship letter review by team | subcommittee | 2024-01-15 |  | review letter, update, send to Ryan
Sponsorship letters emailed/mailed by Jan 20th to: | Ryan | 2024-01-20
DVR | Ryan
Microsoft | ryan
WSECU | ryan
OFM | ryan
DDA | ryan
DSB | ryan
ODHH | ryan
Tribal DVR leaders | ryan
CRPs | ryan
Workforce Development Council | ryan
other sponsors???
processed invoices and send them out to sponsors | Ryan/Emily | 2024-03-30
requested logos from sponsors | Ryan | 2024-03-30
GCDE ESD Awards page updated for this current year

## Feb Tasks
2024 Awards Timeline Workplan
Meeting Date: Feb 1, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Venue Update - confirmed? | subcommittee
Catering and lodging accommodations | subcommittee
Spsonorship Update
Nomination Application Packets; update y/n?
Updates from teams:
marketing & outreach team |  |  |  | marketing timeline
Publications team |  |  |  | update minor edits on program brochure
Event logistis team
judgin panel team
correspondence team
Governor invitation/photo session reponse?
processed invoices and send them out to sponsors | Ryan/emily | 2024-03-30
requested logos from sponsors | Ryan | 2024-03-30

## March Tasks
2024 Awards Timeline Workplan
Meeting Date: March 7, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Venue Update - contract signed?
Catering and lodging accommodations confirmed?
Spsonorship Update
Nomination Application Packets; update y/n?
Updates from teams:
marketing & outreach team
Publications team
Event logistis team
judgin panel team
correspondence team
processed invoices and send them out to sponsors | Ryan/emily | 2024-03-30
requested logos from sponsors | Ryan | 2024-03-30
Update on Governor attendance / photos

## April Tasks
2024 Awards Timeline Workplan
Meeting Date: April 11, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Venue Update - contract signed?
Catering and lodging accommodations confirmed?
Spsonorship Update
Nomination Application Packets; update y/n?
Updates from teams:
marketing & outreach team - local area feedback? |  |  |  | news release for nominations
Publications team - brochure ready?
Event logistis team
judgin panel team
correspondence team
processed invoices and send them out to sponsors | Ryan/emily | 2024-03-30
requested logos from sponsors | Ryan | 2024-03-30
Update on Governor attendance / photos
Review and edit NAP | subcommittee | 2024-04-25
Send NAP to ESD contracts office | Emily | 2024-04-25
Request contract with event location
Sent contract to ESD Contracts Dept
Filled out Per diem Exemption form
Calcuated costs of each meal, hotel stay and per diem for each volunteer member and staff
submitted forms to upper mgmt for approval
returned the travel / per diem form to contracts

## May Tasks
2024 Awards Timeline Workplan
Meeting Date: May 9, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Venue Update - contract signed?
lodging reserved?
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  | 2024-05-30 |  | Launched nominations application packets to WA State; send to listserv
Publications team - brochure sent to comms |  | 2024-05-30
Event logistis team
judgin panel team
correspondence team
Nomination App Updates |  |  |  | ready for launch?
Update on Governor attendance / photos

## June Tasks
2024 Awards Timeline Workplan
Meeting Date: June 13th, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  | 2024-05-30 |  | Launched nominations application packets to WA State; send to listserv
Publications team - |  | 2024-09-01 |  | program book and powerpoint
Event logistis team
judgin panel team
correspondence team
Nomination App Updates
Update on Governor attendance / photos
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?

## July Tasks
2024 Awards Timeline Workplan
Meeting Date: July 11th, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  | 2024-05-30 |  | Launched nominations application packets to WA State; send to listserv
Publications team - |  | 2024-09-01 |  | program book and powerpoint
Event logistis team
judgin panel team |  |  |  | Training date set? Judging dates set?
correspondence team
Nomination App Updates
Update on Governor attendance / photos
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Media release from ESD Comm
Nomination tracking updates
Event Script - volunteers to assist
Trophies ordered?
Meeting Date: July 25th, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  | 2024-05-30 |  | Launched nominations application packets to WA State; send to listserv
Publications team - |  | 2024-09-01 |  | program book and powerpoint
Event logistis team
judgin panel team |  |  |  | juding dates sets?
correspondence team
Nomination App Updates
Update on Governor attendance / photos
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Media release from ESD Comm
Nomination tracking updates
Event Script - volunteers to assist

## Aug Tasks
2024 Awards Timeline Workplan
Meeting Date: August 8th, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  | 2024-05-30 |  | Launched nominations application packets to WA State; send to listserv
Publications team - |  | 2024-09-01 |  | program book and powerpoint
Event logistis team
judgin panel team |  |  |  | Judging dates set?
correspondence team
Nomination App Updates
Update on Governor attendance / photos
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Media release from ESD Comm
Nomination tracking updates
Event Script - volunteers to assist
Trophies ordered?
Registration for board and nominees status
Meeting Date: August 22nd, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  | 2024-05-30 |  | Launched nominations application packets to WA State; send to listserv
Publications team - |  | 2024-09-01 |  | program book and powerpoint
Event logistis team |  |  |  | local volunteers; map from hotel
judgin panel team |  |  |  | judging completed and sent to Emily
correspondence team |  | 2024-08-30 |  | Thank you note templates
Nomination App Updates
Update on Governor attendance / photos
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Media release from ESD Comm
Nomination tracking updates
Event Script - volunteers to assist
Registration for board and nominees

## Sept Tasks
2024 Awards Timeline Workplan
Meeting Date: Sept 5th, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  |  |  | Local newspapers/radio/media updates?
Publications team - |  |  |  | program book, powerpoint, certificates
Event logistis team |  |  |  | see tab
judgin panel team |  |  |  | report out
correspondence team
Update on Governor attendance / photos
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Nomination tracking updates
Trophies ordered? |  | 2024-09-15
Registration for board and nominees status
Dan Thompson Statewide Employment Rally Speaker
GCDE Subcommittee Speakers re: programs
Speakers from DSB, DVR, OHHD etc….
Meeting Date: Sept 26th, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback? |  |  |  | Local newspapers/radio/media updates?
Publications team - |  | 2024-09-30 |  | program book,certificates, powerpoint | Powerpoint sent to MCEE and all presenters
Event logistis team |  |  |  | Day-of Volunteer sign-up - see event logistics tab
correspondence team |  | 2024-08-30 |  | Thank you note templates
Nomination App Updates
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Nomination tracking updates
Registration for board and nominees
Follow up on Speakers?
last minute concerns?

## Oct Tasks
2024 Awards Timeline Workplan
Meeting Date: Oct 3th, 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback?
Publications team -
Event logistis team
judgin panel team
correspondence team
Update on Governor attendance / photos
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Nomination tracking updates
Registration for board and nominees status
Dan Thompson Statewide Employment Rally Speaker
GCDE Subcommittee Speakers re: programs
Speakers from DSB, DVR, OHHD etc….
Meeting Date: Oct 10th , 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Spsonorship Update
Updates from teams:
marketing & outreach team - local area feedback?
Publications team -
Event logistis team
correspondence team
Nomination App Updates
Accommodations arranged? FM. Cart, Screens
Hotel room update? Parking?
Travel forms and Per deim
Nomination tracking updates
Registration for board and nominees
Follow up on Speakers?
last minute concerns?
Meeting Date: Oct 17th , 2024
Deliverables | Person Responsible | Due date | Status | Notes and Steps | Notes from Meeting | Other Feedback
Dinner meeting to work out event logistics

## Event Logistics
Event Logistics
Deliverables | Person Responsible | Status | Notes and Steps | Notes from Meeting | Other Feedback
Volunteers are:
Phill White EMCee
Mary Crago Photographer
Registration Table Volunteers - 4
Nominee Readers - 2
Table Set up 2 - 4
Stage Walk Through / Safety Check - Yvonne & Ryan
Greeters:
Clean up 4 - 6

## Add tasks post nom DL
2024 Awards Timeline Workplan
Deliverables | Person Responsible | Status | Notes and Steps | Notes from Meeting | Other Feedback
Complete judging process | Panelists | in progress | By Fri/Mon | Still working on | Process improvements noted
Draft trophies | Staff | Awaiting above | After judging | Meetings in progress | Will need to be proofed
Nominee highlights weekly (1+) | Staff | in progress | Draft | 1 down, 11 to go | Will need to be proofed
Volunteer signup sheet | Staff | Needs to be sent | Staff to send | Sign up if attending | If help with travel, hotel
Governor's attendance | Staff | Pending | Wait to hear | Should be soon | Late summer/early fall
Send map of route | Staff | Needs to be sent | Staff to send | Should be soon | Yvonne sent to Matt/Ryan
Vocalist confirmation | Yvonne | Pending | Yvonne checking | Should be soon | Update next week
Guest speaker confirmations | Staff | Needs to be sent | Staff to check in | Should be soon | Update next week
Track sponsorship funding/expenses | Staff | Pending | Staff to check in | Should be soon | Update until/post event
Materials review (highlights, trophies, certificates, PPT, program, thank you notes) | Volunteers | in progress | Help needed ongoing | Kevin, Ryan, and Lucas on program | Asks will continue
Event registration | Staff | Needs to be sent | Staff to send | Should be soon | Everyone needs to register (including guests). Let know of process improvements.
Following up with nominees | Volunteers | Needs to be sent | Staff to request | Noted during meeting | regarding photos and spelling confirmations

## Post Awards
2023 Awards Timeline Workplan
Deliverables | Person Responsible | Status | Notes and Steps | Notes from Meeting | Other Feedback
Send thank you notes | Ryan/Yvonne | needs completed | Ryan to draft, Yvonne to approve | Yvonne confirmed 6/5 | Ryan to create template and draft in advance for approval (Yvonne worked on)
Process and track invoices | Emily | in progress | sponsor invoices done, post event needed | Emily to track per 1:1 with RB in late May | in progress
Post photos | Emily | needs completed | after event |  | need captions
Draft media release recipients | Ryan/Yvonne | needs completed | can start after recipients selected |  | still waiting on recipients
Send media release recipients | Comms office | needs completed | wait until after event is over to send |  | will send once drafted
Process member travel | Emily | needs completed | after event for reimbursments |  | after event item